# IPM sample – Embed phase – Curriculum implementation (Implement stage)

## Target audience

The primary audience for this resource is school principals, school leadership teams and school staff in primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. As new syllabuses are introduced, schools may need to engage with different phases based on the requirements of each syllabus. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and system leadership team using the ‘Phases of curriculum implementation’ as guidance. The research base used was NESA’s NSW Curriculum and the department’s What works best in practice. A list of references at the end of this document outlines research that was considered in the development of the ‘Phases of curriculum implementation’.

## Contact

Using subject line ‘Re: IPM sample – Embed phase’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education focus areas: Advance equitable outcomes; Strengthen trust and respect for the teaching profession; Deliver outstanding leadership, teaching and learning.

Alignment to School Excellence Framework (SEF): Learning – Curriculum; Teaching – Learning and development; Leading – School planning, implementation and reporting.

Date created: 14/04/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – Embed phase – Curriculum implementation (Implement stage)

### Rationale

This sample is designed to support the effective implementation of the syllabuses across primary, secondary, central and unique school contexts. School leaders should consider their school’s readiness to progress from the Enact phase to the Embed phase before using this resource. It is designed to help school leaders and teachers strengthen and scale practices and systems for successful curriculum implementation.

### Stage of implementation

| ☐ Plan | ☒ Implement | ☐ Embed |
| --- | --- | --- |

### Activity title

Embed phase – strengthen and scale practices and systems for effective curriculum implementation (Implement)

#### Approximate duration of this activity

| ☐ 1 term | ☐ 2 terms | ☐ 3 terms | ☒ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Curriculum

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Curriculum | Curriculum provision |
| Domain | Element | Theme |
| Teaching | Learning and development | Collaborative practice and feedback |
| Domain | Element | Theme |
| Leading | School planning, implementation and reporting | Continuous improvement |

### Activity description

This is the implement stage of this activity.

This activity will assist schools who have moved into the Embed phase of curriculum implementation. Principals and leadership teams will implement strategies to strengthen curriculum implementation and scale effective practices and systems across the school. This approach aims to support high-quality, evidence-based teaching practices and curriculum resources in alignment with Our Plan for NSW Public Education.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Effective teaching and learning | Implement the teaching and learning cycle to plan, teach and assess programs that address syllabus outcomes. Student data will be used to refine programs, ensuring they are dynamic and responsive to the learning needs of all students including the literacy and numeracy demands of the syllabus. |
| Task title 2 | Task description 2 |
| Fostering collaborative planning and professional dialogue | Provide opportunities for collaborative planning, programming and meaningful professional dialogue to be embedded into school-wide practices. This will allow teachers to share expertise, reflect on student outcomes and continuously improve curriculum implementation. |
| Task title 3 | Task description 3 |
| Differentiated support and professional learning | Leadership team provides differentiated support and ongoing professional learning to teachers as needed. This targeted approach ensures that all teachers receive the resources and training necessary to effectively implement the curriculum. |
| Task title 4 | Task description 4 |
| Collaborate with other schools, networks and Communities of Practice (CoP) | Engage with other schools and communities of practice to share insights, exchange resources and refine teaching practices. This collaboration will strengthen curriculum implementation and promote continuous improvement. |
| Task title 5 | Task description 5 |
| Sustaining a culture of reflective practice | Sustain a culture that encourages meaningful collaboration through peer observations, co-teaching and shared planning. Teachers regularly review evidence, reflect on practice, and adapt strategies to optimise learning for all students. |

### Resources and funding

Timetabling could be maximised to allow for teachers to meet for collaborative planning time and collegial discussions. Professional learning funds may also be used to support this. Staff meeting time could be used to engage with professional learning that has been identified in the tasks.

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent have effective curriculum implementation practices been embedded within the school to support long term sustainable and continuous improvement? | Teaching programs, student assessment data, collegial discussion notes, professional learning plans, evidence of explicit teaching embedded in learning programs and classroom practice, community of practice notes and data, surveys and focus group results. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au and the NSW Curriculum website https://curriculum.nsw.edu.au.

Research that was considered when developing the ‘Phases of curriculum implementation’:

Albers B and Pattuwage L (2017) ‘Implementation in Education: Findings from a Scoping Review', Melbourne: Evidence for Learning, accessed 9 July 2025.

Dao L (2021) ‘Challenges and enablers encountered by a curriculum leadership team in implementing the national curriculum in one Australian school’, Leading and Managing, 27(1):79–98, accessed 9 July 2025.

Gouëdard P, Pont B, Hyttinen S and Huang P (2020) ‘Curriculum reform: A literature review to support effective implementation', OECD Education Working Papers, no. 239:20–45, https://doi.org/10.1787/efe8a48c-en, accessed 9 July 2025.

Jones C and Anderson M (2001) Managing curriculum change [PDF 119 KB], Learning and Skills Development Agency, accessed 9 July 2025.

Sharples J, Albers B, Fraser S, Deeble M and Vaughan T (2019) ‘Putting Evidence to Work: A School’s Guide to Implementation', Evidence for Learning, accessed 9 July 2025.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.