# IPM sample – Enact phase – Curriculum implementation (Implement stage)

## Target audience

The primary audience for this resource is school principals, school leadership teams and school staff in primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. As new syllabuses are introduced, schools may need to engage with different phases based on the requirements of each syllabus. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and system leadership team using the ‘Phases of curriculum implementation’ as guidance. The research base used was NESA’s NSW Curriculum and the department’s What works best in practice. A list of references at the end of this document outlines research that was considered in the development of the ‘Phases of curriculum implementation’.

## Contact

Using subject line ‘Re: IPM sample – Enact phase’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education focus areas: Advance equitable outcomes; Strengthen trust and respect for the teaching profession; Deliver outstanding leadership, teaching and learning.

Alignment to School Excellence Framework (SEF): Learning – Curriculum; Teaching – Learning and development; Leading – Educational leadership.

Date created: 14/04/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – Enact phase – Curriculum implementation (Implement stage)

### Rationale

This sample is designed to support the effective implementation of the syllabuses across primary, secondary, central and unique school contexts. School leaders should consider their school’s readiness to progress from the Engage phase to the Enact phase before using this resource. School leaders and teachers can use this resource to guide the introduction of teaching, assessing and reporting practices of syllabuses they are implementing, while also evaluating and refining their practices and systems for continuous improvement.

### Stage of implementation

| ☐ Plan | ☒ Implement | ☐ Embed |
| --- | --- | --- |

### Activity title

Enact phase – teach, assess and report using the new syllabus and evaluative curriculum implementation (Implement)

#### Approximate duration of this activity

| ☐ 1 term | ☐ 2 terms | ☐ 3 terms | ☒ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Curriculum

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Curriculum | Curriculum provision |
| Domain | Element | Theme |
| Teaching | Learning and development | Professional learning |
| Domain | Element | Theme |
| Teaching | Learning and development | Collaborative practice and feedback |
| Domain | Element | Theme |
| Leading | Educational leadership | Leading teaching and learning |

### Activity description

This is the implement stage of this activity.

This activity will assist schools who have moved into the Enact phase of curriculum implementation. Teachers will begin to effectively implement curriculum into classroom teaching and learning programs, while leadership teams evaluate the effectiveness of these practices and systems. This approach aims to support high-quality, evidence-based teaching practices and curriculum resources in alignment with Our Plan for NSW Public Education.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Implementing teaching programs aligned with the new curriculum | Teachers plan, program and deliver teaching programs that are aligned with the new syllabus outcomes, and are responsive to the diverse learning needs of students and syllabus requirements, including the literacy and numeracy demands. |
| Task title 2 | Task description 2 |
| Collaborative planning and programming | Stage and faculty teams engage in professional discussion and collaborate during planning sessions to adapt teaching resources (Planning, programming and assessing K–6 resources/Planning, programming and assessing 7–12 resources). This collaboration ensures that teaching materials are aligned to student and contextual need. |
| Task title 3 | Task description 3 |
| Using data to inform practice | Stage and faculty teams engage in regular reviews of student data to inform and enhance teaching practices. Use the Effective assessment practices guide and Assessment to support teachers to choose suitable assessment strategies and understand how to use assessment data effectively. |
| Task title 4 | Task description 4 |
| Targeted support and professional learning | The leadership team provides differentiated support and professional learning tailored to teachers’ needs as they implement curriculum, fostering a culture of continuous improvement. This professional learning may include microlearning modules or Curriculum planning for every student in every classroom K–12. |
| Task title 5 | Task description 5 |
| Engaging with networks and Communities of Practice (CoP) | Staff collaborate with other schools and professional learning networks such as Curriculum Reform Communities (CRC) networks and CoPs to share insights, refine teaching practice, and address common challenges during curriculum implementation. |
| Task title 6 | Task description 6 |
| Communicating with parents and the community | Conduct information sessions and provide regular updates through newsletters to keep parents, carers and the community informed about curriculum changes and their implications for student learning. (Communicating with parents and carers, Reporting to parents). |

### Resources and funding

Timetabling could be maximised to allow for teachers to meet for collaborative planning time and collegial discussions. Professional learning funds may also be used to support this. Staff meeting time could be used to engage with professional learning that has been identified in the tasks.

Planning, programming and assessing K–6 resources

Planning, programming and assessing 7–12 resources

Effective assessment practices guide

Assessment

Curriculum planning for every student in every classroom K-12

Explicit teaching

CRC networks

Communicating with parents and carers

Reporting to parents

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent have staff effectively implemented the curriculum to meet the contextual needs of their school and students? | Teaching programs, student assessment data, collegial discussion notes, professional learning plans, community of practice notes and data, parent communication documentation, survey and focus group data. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au and the NSW Curriculum website https://curriculum.nsw.edu.au.

Research that was considered when developing the ‘Phases of curriculum implementation’:

Albers B and Pattuwage L (2017) ‘Implementation in Education: Findings from a Scoping Review', Melbourne: Evidence for Learning, accessed 9 July 2025.

Dao L (2021) ‘Challenges and enablers encountered by a curriculum leadership team in implementing the national curriculum in one Australian school’, Leading and Managing, 27(1):79–98, accessed 9 July 2025.

Gouëdard P, Pont B, Hyttinen S and Huang P (2020) ‘Curriculum reform: A literature review to support effective implementation', OECD Education Working Papers, no. 239:20–45, https://doi.org/10.1787/efe8a48c-en, accessed 9 July 2025.

Jones C and Anderson M (2001) Managing curriculum change [PDF 119 KB], Learning and Skills Development Agency, accessed 9 July 2025.

Sharples J, Albers B, Fraser S, Deeble M and Vaughan T (2019) ‘Putting Evidence to Work: A School’s Guide to Implementation', Evidence for Learning, accessed 9 July 2025.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.