# IPM sample – Enact phase – Curriculum implementation (Plan stage)

## Target audience

The primary audience for this resource is school principals, school leadership teams and school staff in primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. As new syllabuses are introduced, schools may need to engage with different phases based on the requirements of each syllabus. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and system leadership team using the ‘Phases of curriculum implementation’ as guidance. The research base used was NESA’s NSW Curriculum and the department’s What works best in practice. A list of references at the end of this document outlines research that was considered in the development of the ‘Phases of curriculum implementation’.

## Contact

Using subject line ‘Re: IPM sample – Enact phase’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education focus areas: Advance equitable outcomes; Strengthen trust and respect for the teaching profession; Deliver outstanding leadership, teaching and learning.

Alignment to School Excellence Framework (SEF): Learning – Curriculum; Teaching – Learning and development; Leading – Educational leadership.

Date created: 14/04/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – Enact phase – Curriculum implementation (Plan stage)

### Rationale

This sample is designed to support the effective implementation of syllabuses across primary, secondary, central and unique school contexts. School leaders should consider their school’s readiness to progress from the Engage phase to the Enact phase before using this resource. School leaders and teachers can use this resource to guide the introduction of teaching, assessing and reporting practices of syllabuses they are implementing, while also evaluating and refining their practices and systems for continuous improvement.

### Stage of implementation

| ☒ Plan | ☐ Implement | ☐ Embed |
| --- | --- | --- |

### Activity title

Enact phase – teach, assess and report using the new syllabus and evaluative curriculum implementation (Plan)

#### Approximate duration of this activity

| ☐ 1 term | ☒ 2 terms | ☐ 3 terms | ☐ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Curriculum

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Curriculum | Curriculum provision |
| Domain | Element | Theme |
| Teaching | Learning and development | Professional learning |
| Domain | Element | Theme |
| Leading | Educational leadership | Leading teaching and learning |

### Activity description

This is the plan stage of this activity.

This activity will assist schools who have moved into the Enact phase of curriculum implementation. Principals and leadership teams will plan how curriculum will be effectively implemented into classroom teaching and learning programs, while also planning for the evaluation of these actions to enhance practices and systems. This approach aims to support high-quality, evidence-based teaching practices and curriculum resources in alignment with Our Plan for NSW Public Education.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Identify staff, student and resource needs as required for the Enact phase | Use the Phases of curriculum implementation journeys to identify role-specific guidance for the Enact phase. Use the Curriculum implementation planning template to determine staff and student needs. Consider required resources, budget and time allocations to support this phase of curriculum implementation. |
| Task title 2 | Task description 2 |
| Build leadership capabilities | Middle leaders and aspiring leaders enhance their curriculum leadership capabilities by completing the Leading effective curriculum implementation (Modules 3, 4 and 5) professional learning. |
| Task title 3 | Task description 3 |
| Establishing structures for collaborative planning | The leadership team develop timetables and meeting structures that enable stage and faculty teams to collaborate during the Enact phase. This will ensure time is allocated for shared planning and programming. |
| Task title 4 | Task description 4 |
| Reviewing and preparing assessment processes | Teachers and the leadership team review current assessment processes while reflecting on the Curriculum policy standards. Using the Effective assessment practices guide and the Curriculum planning and programming, assessing and reporting to parents K-12 policy, identify areas requiring adjustment to ensure alignment with the new curriculum. |
| Task title 5 | Task description 5 |
| Mapping further professional learning needs | Leadership team and staff identify further professional learning needs related to the new curriculum. The leadership team coordinate access to relevant Professional learning – curriculum K–12 resources to enhance teaching and learning. |
| Task title 6 | Task description 6 |
| Preparing for inclusive curriculum delivery | Staff engage with the Curriculum planning for every student – advice, to ensure they are optimising learning opportunities for every student. They may engage in the Curriculum planning for every student in every classroom microlearning modules to further strengthen their practice. |
| Task title 7 | Task description 7 |
| Planning updates to parent reporting | The leadership team and staff review reporting requirements as outlined in the Curriculum planning and programming, assessing and reporting to parents K-12 policy to identify necessary updates to documentation and processes in preparation for communicating changes with parents and caregivers. |
| Task title 8 | Task description 8 |
| Developing a communication plan | The leadership team outlines a communication strategy to inform the school community about upcoming curriculum changes. This plan will guide clear, consistent messaging throughout the Embed phase (Communicating with parents and carers/Reporting to parents). |

### Resources and funding

This stage of the IPM focuses on leadership planning. Timetabling could be maximised to allow for the leadership team to meet, or professional learning funds could be used to release the leadership team.

Phases of curriculum implementation journeys

Curriculum implementation planning template

Leading effective curriculum implementation

Curriculum policy standards

Effective assessment practices guide

Curriculum planning and programming, assessing and reporting to parents K-12 policy

Professional learning – curriculum K–12

Curriculum planning for every student – advice

Curriculum planning for every student in every classroom microlearning modules

Communicating with parents and carers

Reporting to parents

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent is the school prepared to enact effective implementation of the curriculum, and what needs must be addressed to ensure continued engagement? | Curriculum implementation planning template, professional learning plan, collaborative timetabling, assessment and reporting timeline and updated school procedures, updated reporting template, parent communication strategy, survey and focus group data. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au and the NSW Curriculum website https://curriculum.nsw.edu.au.

Research that was considered when developing the ‘Phases of curriculum implementation’:

Albers B and Pattuwage L (2017) ‘Implementation in Education: Findings from a Scoping Review', Melbourne: Evidence for Learning, accessed 9 July 2025.

Dao L (2021) ‘Challenges and enablers encountered by a curriculum leadership team in implementing the national curriculum in one Australian school’, Leading and Managing, 27(1):79–98, accessed 9 July 2025.

Gouëdard P, Pont B, Hyttinen S and Huang P (2020) ‘Curriculum reform: A literature review to support effective implementation', OECD Education Working Papers, no. 239:20–45, https://doi.org/10.1787/efe8a48c-en, accessed 9 July 2025.

Jones C and Anderson M (2001) Managing curriculum change [PDF 119 KB], Learning and Skills Development Agency, accessed 9 July 2025.

Sharples J, Albers B, Fraser S, Deeble M and Vaughan T (2019) ‘Putting Evidence to Work: A School’s Guide to Implementation', Evidence for Learning, accessed 9 July 2025.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.