# IPM sample – Engage phase – Curriculum implementation (Implement stage)

## Target audience

The primary audience for this resource is school principals, school leadership teams and school staff in a primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. As new syllabuses are introduced, schools may need to engage with different phases based on the requirements of each syllabus. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and system leadership team using the ‘Phases of curriculum implementation’ as guidance. The research base used was NESA’s NSW Curriculum and the department’s What works best in practice. A list of references at the end of this document outlines research that was considered in the development of the ‘Phases of curriculum implementation’.

## Contact

Using subject line ‘Re: IPM sample – Engage phase’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education focus areas: Advance equitable outcomes; Strengthen trust and respect for the teaching profession; Deliver outstanding leadership, teaching and learning.

Alignment to School Excellence Framework (SEF): Learning – Curriculum; Teaching – Learning and development; Leading – Educational leadership.

Date created: 14/04/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – Engage phase – Curriculum implementation (Implement stage)

### Rationale

This sample is for use in primary, secondary, central or small and unique school contexts in the initial stages of new syllabus implementation. School leaders and teachers will explore aspects of the new syllabus or syllabuses they are implementing to identify and plan changes required for effective implementation. School leaders and teachers will participate in a variety of activities supported by new and existing resources.

### Stage of implementation

| ☐ Plan | ☒ Implement | ☐ Embed |
| --- | --- | --- |

### Activity title

Engage phase – identify and plan for changes required for effective curriculum implementation (Implement)

#### Approximate duration of this activity

| ☐ 1 term | ☒ 2 terms | ☐ 3 terms | ☐ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Curriculum

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Curriculum | Curriculum provision |
| Domain | Element | Theme |
| Teaching | Learning and development | Professional learning |
| Domain | Element | Theme |
| Leading | Educational leadership | Leading teaching and learning |

### Activity description

This is the implement stage of this activity.

This activity will support schools in the Engage phase of curriculum implementation. Principals and leadership teams will guide their school in exploring the new syllabus they are implementing and plan necessary changes to ensure teaching and learning programs align with student needs and syllabus requirements. This will support the development of high-quality, evidence-based teaching practices and curriculum resources aligning with Our Plan for NSW Public Education.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Build leadership capabilities | Middle leaders and aspiring leaders enhance their capabilities by completing the Leading effective curriculum implementation (Modules 1 and 2) professional learning. |
| Task title 2 | Task description 2 |
| Engage in collaborative networks | Identify opportunities to collaborate with other school leaders through local networks, such as Curriculum Reform Communities (CRCs), to share insights and best practice. |
| Task title 3 | Task description 3 |
| Deepen understanding of NSW Curriculum | Curriculum leadership team lead staff in exploring the NSW curriculum to deepen their understanding of the evidence underpinning the new syllabus, including the literacy and numeracy demands. Staff unpack the resources and teaching advice for the syllabus. |
| Task title 4 | Task description 4 |
| Access and deliver evidence-based professional learning | The curriculum leadership team access and facilitate evidence-based professional learning to familiarise all staff with the new syllabus. Possible resources include: NESA syllabus introduction videos Curriculum planning for every student in every classroom NSW Department of Education microlearning modules available through MyPL. Staff complete exit slips after engaging in professional learning to reflect on understanding. |
| Task title 5 | Task description 5 |
| Engage staff in reflective practice | Ensure that all staff reflect on the Engage phase questions to foster collaborative discussion about curriculum implementation. As appropriate, record key discussion points and address any areas that require further investigation. |
| Task title 6 | Task description 6 |
| Monitor staff understanding | Leadership team to reflect on professional learning exit slips to assess staff understanding of the pedagogical changes associated with the new curriculum. |

### Resources and funding

Timetabling could be maximised to allow for teachers to meet for collaborative professional learning time and use professional learning funds. Staff meeting time could also be used to engage with professional learning that has been identified in the tasks.

Leading effective curriculum implementation

Curriculum Reform Communities

NSW Curriculum

NESA syllabus introduction videos

Curriculum planning for every student

NSW Department of Education microlearning modules available through MyPL

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent have staff understood the changes to the syllabus and the evidence base underpinning these changes, and how prepared are they to effectively implement the curriculum? | Professional learning exit slips, pre and post professional learning survey data, focus group data. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au and the NSW Curriculum website https://curriculum.nsw.edu.au.

Research that was considered when developing the ‘Phases of curriculum implementation’:

Albers B and Pattuwage L (2017) ‘Implementation in Education: Findings from a Scoping Review', Melbourne: Evidence for Learning, accessed 9 July 2025.

Dao L (2021) ‘Challenges and enablers encountered by a curriculum leadership team in implementing the national curriculum in one Australian school’, Leading and Managing, 27(1):79–98, accessed 9 July 2025.

Gouëdard P, Pont B, Hyttinen S and Huang P (2020) ‘Curriculum reform: A literature review to support effective implementation', OECD Education Working Papers, no. 239:20–45, https://doi.org/10.1787/efe8a48c-en, accessed 9 July 2025.

Jones C and Anderson M (2001) Managing curriculum change [PDF 119 KB], Learning and Skills Development Agency, accessed 9 July 2025.

Sharples J, Albers B, Fraser S, Deeble M and Vaughan T (2019) ‘Putting Evidence to Work: A School’s Guide to Implementation', Evidence for Learning, accessed 9 July 2025.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.