# IPM sample – engaging parents, caregivers and community in transition from primary to high school (Implement stage)

## Target audience

The primary audience for this resource is principals, school leadership teams and school staff in primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and System Leadership team, informed by research such as Transition to high school – What Works Best in practice (CESE 2024). The transition from primary to high school is significant and can impact students’ emotional wellbeing and academic growth. Research shows that a successful transition supports stronger engagement, academic progress and increased school completion rates. To support students during this transition period, it is essential to maintain continuity in curriculum and teaching practices across both educational stages.

## Contact

Using subject line ‘Re: IPM sample – Transition from primary to high school’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education areas: Advance equitable outcomes, opportunities and experiences; Deliver outstanding leadership, teaching and learning; Strengthen student wellbeing and development.

Alignment to School Excellence Framework: Learning – Learning culture; Teaching – Data skills and use; Leading – Educational leadership.

Date created: 8/05/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – engaging parents, caregivers and community in transition from primary to high school (Implement stage)

### Rationale

Engaging parents, caregivers and the community in the transition from primary to high school supports continuity of learning. Meaningful collaboration creates a supportive environment, improves communication between home and school, making the transition smoother for students. Involving families provides key information about the curriculum and what to expect, empowering them to support their children throughout transition. Community engagement builds networks that enhance students’ confidence, wellbeing and academic success as they navigate this important stage in their education.

### Stage of implementation

| ☐ Plan | ☒ Implement | ☐ Embed |
| --- | --- | --- |

### Activity title

Developing strong engagement with parents and the community to improve continuity of learning from primary to high school (Implement)

#### Approximate duration of this activity

| ☐ 1 term | ☐ 2 terms | ☐ 3 terms | ☒ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Parent engagement

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Learning culture | Transitions and continuity of learning |
| Domain | Element | Theme |
| Teaching | Data skills and use | Data use in planning |
| Domain | Element | Theme |
| Leading | Educational leadership | Community engagement |

### Activity description

This is the implement stage of this activity.

This activity supports schools to implement plans for strengthened engagement with parents, caregivers and the broader community during the transition from primary to high school. It promotes shared responsibility for student success by improving communication, building trust and creating supportive networks around learners. By actively involving families and community partners, schools can enhance continuity of learning, ease the transition experience and support student wellbeing and achievement. This activity aligns with Our Plan for NSW Public Education by advancing equitable outcomes, delivering outstanding leadership, teaching and learning, and strengthening student wellbeing.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Establish connections across schools | Organise community events for primary and high school parents and caregivers to meet and establish a connection. Facilitate discussions for community members to share experiences, build relationships and foster a supportive network. This will strengthen the transition process and promote continuity of learning. |
| Task title 2 | Task description 2 |
| Engage with the community | Initiate community engagement activities (identified in the community engagement plan) such as workshops, information sessions and cultural events. Invite community members, parents and caregivers to connect with both primary and secondary schools. These events should celebrate community diversity, promote family-school connections and support continuity of learning. |
| Task title 3 | Task description 3 |
| Involve Parents and Citizens (P&C) Associations | Encourage high school staff to attend primary P&C meetings to present on school culture and transition activities. This visibility will strengthen relationships across contexts and promote open communication, ensuring parents and caregivers feel connected across contexts. |
| Task title 4 | Task description 4 |
| Facilitate student interaction | - Create opportunities for Stage 4 students from partner primary schools to visit and share their experiences of transition with Stage 3 students. This peer interaction can help build excitement for high school and foster a positive outlook on the transition to high school. Communicate this activity with the community, parents and caregivers. |
| Task title 5 | Task description 5 |
| Enhance communication about transition from primary to high school across contexts | - Develop and distribute regular communications that outline available transition activities and opportunities across primary and secondary contexts. Use a range of communication methods to inform the community, parents and caregivers, encouraging engagement in events and activities. |
| Task title 6 | Task description 6 |
| Gather feedback from participants | After engagement activities, collect feedback from the community, parents, caregivers and students to evaluate successes and identify areas for improvement. Use this feedback to inform future activities and highlight the importance of working in partnership with the community to strengthen transition to high school. |

### Resources and funding

Timetabling could be maximised to allow for teachers across schools to meet, or professional learning funds could be used to release the leadership team. Additional time may be required to organise cross-school visits with students. If possible, consideration could be given to use funding for Student Learning Support Officers (SLSOs) and/or Community Liaison Officers (CLOs) to support and strengthen engagement during transition activities.

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent have schools effectively engaged parents, caregivers and the broader community to strengthen relationships, support student transition and enhance continuity of learning? | Community involvement planning documents, P&C minutes, feedback from events. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au/ and the NSW Curriculum website https://curriculum.nsw.edu.au.

Anderson LW, Jacobs J, Schramm S and Splittgerber F (2000) ‘School transitions: beginning of the end or a new beginning?’, International Journal of Educational Research, 33(4):325–339, accessed 17 April 2024.

CESE (Centre for Education Statistics and Evaluation) (2024) Transition to high school – What Works Best in practice, NSW Department of Education.

Galton M and McLellan R (2017) ‘A transition Odyssey: pupils’ experiences of transfer to secondary school across five decades’, Research Papers in Education, 33(2):1–23, accessed 17 April 2024.

Martin AJ, Collie RJ, Stephan M, Flesken A, Halcrow F and McCourt B (2024) ‘The role of teaching support in assisting students’ transition to high school’, Learning and Individual Differences, 109(102382), accessed 17 April 2024.

Martin AJ, Collie RJ, Stephan M, Flesken A, Halcrow F and McCourt B (2024) ‘What is the role of teaching support in students’ motivation and engagement trajectories during adolescence? A four-year latent growth modelling study’, Learning and Instruction, 92(101910), accessed 17 April 2024.

Sniedze S, Felgate R, O’Grady E, Buckley S and Lietz P (2021) ‘What Australian students say about transition to secondary school. Final report’, Australian Council for Educational Research, accessed 17 April 2024.

Symonds JE and Galton M (2014) ‘Moving to the next school at age 10–14 years: an international review of psychological development at school transition’, Review of Education, 2(1):1–27, accessed 17 April 2024.

Van Rens M, Haelermans C, Groot W and van den Brink HM (2018) ‘Facilitating a Successful Transition to Secondary School: (How) Does it Work? A Systematic Literature Review’, Adolescent Research Review, 3:43–56, accessed 17 April 2024.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.