# IPM sample – transition from primary to high school (Embed stage)

## Target audience

The primary audience for this resource is principals, school leadership teams and school staff in primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and System Leadership team, informed by research such as Transition to high school – What Works Best in practice (CESE 2024). The transition from primary to high school is significant and can impact students’ emotional wellbeing and academic growth. Research shows that a successful transition supports stronger engagement, academic progress and increased school completion rates. To support students during this transition period, it is essential to maintain continuity in curriculum and teaching practices across both educational stages.

## Contact

Using subject line ‘Re: IPM sample – Transition from primary to high school’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education areas: Advance equitable outcomes, opportunities and experiences; Deliver outstanding leadership, teaching and learning; Strengthen student wellbeing and development.

Alignment to School Excellence Framework: Learning – Learning culture, Curriculum.

Date created: 8/05/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – transition from primary to high school
(Embed stage)

### Rationale

This sample is designed to support collaboration between schools and build teachers’ understanding of the Stage 3 and 4 syllabuses. School leaders and teachers will engage in a variety of activities, drawing on both new and existing resources, to strengthen continuity of learning and support a smooth transition from primary to high school. Effective transition practices enable teachers to identify what students know and can do, ensuring learning is appropriately extended and supported as they move through stages of schooling.

### Stage of implementation

| ☐ Plan | ☐ Implement | ☒ Embed |
| --- | --- | --- |

### Activity title

Developing strong collaborative partnerships across school contexts to improve continuity of learning from primary to high school (Embed).

#### Approximate duration of this activity

| ☐ 1 term | ☐ 2 terms | ☒ 3 terms | ☐ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Curriculum

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Learning culture | Transitions and continuity of learning |
| Domain | Element | Theme |
| Learning | Curriculum | Curriculum provision |
| Domain | Element | Theme |

### Activity description

This is the embed stage of this activity.

This activity supports schools in embedding effective transition from primary to high school, fostering continuity of learning through collaboration between primary and secondary contexts. It promotes a shared understanding of student needs, strengthens relationships, and enables teachers to build on students' existing knowledge and skills. This activity aligns with Our Plan for NSW Public Education by focusing on advancing equitable outcomes, ensuring all students have access to opportunities and experiences; delivering outstanding leadership, teaching and learning; and enhancing student wellbeing and development during this critical transition period.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Establish ongoing collaboration framework | Create a formal process for ongoing collaboration between primary and secondary staff, including regular meetings and shared professional learning opportunities, reinforcing the shared vision. |
| Task title 2 | Task description 2 |
| Develop sustainability plans | Formulate strategies for sustaining initiatives and relationships established during the transition process. Integrate successful practices into school procedures across the network to enhance continuity of learning. |
| Task title 3 | Task description 3 |
| Conduct yearly survey for continuous improvement | Plan to conduct annual follow-up surveys to assess the effectiveness of the transition process and identify areas for ongoing improvement. |
| Task title 4 | Task description 4 |
| Review and revise transition milestones | Regularly revisit transition milestones based on feedback and data analysis, ensuring they remain relevant and effective in supporting student learning. |
| Task title 5 | Task description 5 |
| Celebrate successes | Host events to celebrate the success of transition initiatives. Recognise contributions from all stakeholders to foster a sense of community and shared achievement. |
| Task title 6 | Task description 6 |
| Share best practices and outcomes | Share findings and successful practices across the school network. This can include presentations at staff meetings, conferences and other forms of communication to reinforce connections. |
| Task title 7 | Task description 7 |
| Create a resource hub | Develop a shared digital folder, or access resources on the Universal Resources Hub, including materials, teaching strategies and success stories related to the Year 6 to Year 7 transition process. |
| Task title 8 | Task description 8 |
| Foster relationships with families | Continue engaging families and community members with information sessions and resources to support an enhanced understanding of effective transition. |

### Resources and funding

Timetabling could be maximised to allow for the teachers across schools to meet, or professional learning funds could be used to release the leadership team.

Consideration could be given to use funding for Student Learning Support Officers (SLSOs) and/or Community Liaison Officers (CLOs) to support and strengthen engagement during transition activities.

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent have sustainable practices and collaboration frameworks been embedded to ensure ongoing improvement and continuity of learning in the primary to high school transition? | Sustainability plans, survey data, milestone tracking results, communication with parents and carers. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au/ and the NSW Curriculum website https://curriculum.nsw.edu.au.

Anderson LW, Jacobs J, Schramm S and Splittgerber F (2000) ‘School transitions: beginning of the end or a new beginning?’, International Journal Of Educational Research, 33(4):325–339, accessed 17 April 2024.

CESE (Centre for Education Statistics and Evaluation) (2024) Transition to high school – What Works Best in practice, NSW Department of Education.

Galton M and McLellan R (2017) ‘A transition Odyssey: pupils’ experiences of transfer to secondary school across five decades’, Research Papers in Education, 33(2):1–23, accessed 17 April 2024.

Martin AJ, Collie RJ, Stephan M, Flesken A, Halcrow F and McCourt B (2024) ‘The role of teaching support in assisting students’ transition to high school’, Learning and Individual Differences, 109(102382), accessed 17 April 2024.

Martin AJ, Collie RJ, Stephan M, Flesken A, Halcrow F and McCourt B (2024) ‘What is the role of teaching support in students’ motivation and engagement trajectories during adolescence? A four-year latent growth modelling study’, Learning and Instruction, 92(101910), accessed 17 April 2024.

Sniedze S, Felgate R, O’Grady E, Buckley S and Lietz P (2021) ‘What Australian students say about transition to secondary school. Final report’, Australian Council for Educational Research, accessed 17 April 2024.

Symonds JE and Galton M (2014) ‘Moving to the next school at age 10–14 years: an international review of psychological development at school transition’, Review of Education, 2(1):1–27, accessed 17 April 2024.

Van Rens M, Haelermans C, Groot W and van den Brink HM (2018) ‘Facilitating a Successful Transition to Secondary School: (How) Does it Work? A Systematic Literature Review’, Adolescent Research Review, 3:43–56, accessed 17 April 2024.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.