# IPM sample – transition from primary to high school (Implement stage)

## Target audience

The primary audience for this resource is principals, school leadership teams and school staff in primary, secondary, central or small and unique school contexts. It may also be adopted and adapted by all other school types.

## When and how to use

Sample implementation and progress monitoring (IPM) plans are designed to help schools implement their School Excellence Plans (SEP). These samples are organised into 3 stages: Plan, Implement and Embed. Schools can select the stage that best aligns with their current needs and adjust the activities or tasks to suit their specific context and the syllabuses they are implementing. The sequence of activities may change throughout the year based on ongoing evaluation, with adjustments made based on analysis and feedback.

## Research base

This resource was developed by the School and System Leadership team, informed by research such as Transition to high school – What Works Best in practice (CESE 2024). The transition from primary to high school is significant and can impact students’ emotional wellbeing and academic growth. Research shows that a successful transition supports stronger engagement, academic progress and increased school completion rates. To support students during this transition period, it is essential to maintain continuity in curriculum and teaching practices across both educational stages.

## Contact

Using subject line ‘Re: IPM sample – transition from primary to high school’, email questions or comments about this resource to contactcurriculumimplementation@det.nsw.edu.au.

Alignment to system priorities and/or needs: Our Plan for NSW Public Education areas: Advance equitable outcomes, opportunities and experiences; Deliver outstanding leadership, teaching and learning; Strengthen student wellbeing and development.

Alignment to School Excellence Framework: Learning – Learning culture, Curriculum.

Date created: 8/05/2025		Last updated: 15/07/2025

Anticipated review: ☐ Half yearly	☒ Annually

## IPM sample – transition from primary to high school (Implement stage)

### Rationale

This sample is designed to support collaboration between schools and build teachers’ understanding of the Stage 3 and 4 syllabuses. School leaders and teachers will engage in a variety of activities, drawing on both new and existing resources, to strengthen continuity of learning and support a smooth transition from primary to high school. Effective transition practices enable teachers to identify what students know and can do, ensuring learning is appropriately extended and supported as they move through stages of schooling.

### Stage of implementation

| ☐ Plan | ☒ Implement | ☐ Embed |
| --- | --- | --- |

### Activity title

Developing strong collaborative partnerships across school contexts to improve continuity of learning from primary to high school (Implement).

#### Approximate duration of this activity

| ☐ 1 term | ☐ 2 terms | ☐ 3 terms | ☒ 4 terms |
| --- | --- | --- | --- |

#### Focus area

Curriculum

#### SEF alignment

| Domain | Element | Theme |
| --- | --- | --- |
| Learning | Learning culture | Transitions and continuity of learning |
| Domain | Element | Theme |
| Learning | Curriculum | Curriculum provision |
| Domain | Element | Theme |

### Activity description

This is the implement stage of this activity.

This activity supports schools in implementing effective transition from primary to high school, fostering continuity of learning through collaboration between primary and secondary contexts. It promotes a shared understanding of student needs, strengthens relationships, and enables teachers to build on students' existing knowledge and skills. This activity aligns with Our Plan for NSW Public Education by focusing on advancing equitable outcomes, ensuring all students have access to opportunities and experiences; delivering outstanding leadership, teaching, and learning; and enhancing student wellbeing and development during this critical transition period.

### Tasks

| Task title 1 | Task description 1 |
| --- | --- |
| Facilitate teacher collaboration sessions and develop a shared focus | Schedule regular meetings for Stage 3 and Stage 4 teachers to collaborate on pedagogical approaches and share best practice across school contexts. Reflecting on the shared vision, identify a focus, such as a curriculum or wellbeing initiative, to guide transition activities and enhance continuity of learning across contexts. |
| Task title 2 | Task description 2 |
| Create shared student profiles | Develop a system for sharing student profiles between Stage 3 and Stage 4 teachers, including strengths, challenges and learning preferences, to support continuity of learning. |
| Task title 3 | Task description 3 |
| Examine student work samples for consistency | Review student work samples from Stage 3 and Stage 4. Analyse samples to identify progress and areas needing support. Determine opportunities to improve connections and understanding of student needs between stages and across school contexts. |
| Task title 4 | Task description 4 |
| Organise transition workshops for teachers | Facilitate workshops for primary and secondary school teachers focused on the shared focus, such as curriculum. Emphasise evidence-based pedagogical approaches for effective transition and promote consistency in teaching practices. |
| Task title 5 | Task description 5 |
| Provide opportunities for primary students to connect with the high school | Organise regular activities for primary students to authentically engage with the high school, fostering relationships through collaborative projects, events and classroom experiences. Facilitate ongoing opportunities to connect with high school staff and students, promoting a sense of community. |
| Task title 6 | Task description 6 |
| Implement a high school orientation program for Year 6 students | Plan a dedicated high school orientation program for Stage 3 students. Include opportunities for students to meet Year 7 teachers and participate in orientation sessions to build connections. The program will support a smooth transition and familiarisation with the high school environment. |
| Task title 7 | Task description 7 |
| Gather and analyse feedback | Collect feedback from teachers and students after transition activities. Use this information to refine processes, ensuring ongoing improvement and alignment with the shared vision. |
| Task title 8 | Task description 8 |
| Monitor and evaluate progress | Regularly review progress against the transition logic model and evaluation framework, using data to inform decision making. |

### Resources and funding

Timetabling could be maximised to allow for the teachers across schools to meet, or professional learning funds could be used to release the leadership team.

Staff could access curriculum professional learning such as microlearning modules to deepen understanding of the evidence base for each syllabus if required.

Consideration could be given to use funding for Student Learning Support Officers (SLSOs) and/or Community Liaison Officers (CLOs) to support and strengthen engagement during transition activities.

### Evaluation and evidence

Outline how this activity will be evaluated using QDAI:

key evaluation question (Q) aligned to the achievement of the activity

list the data (D) sources aligned to the question to show achievement of the activity.

Note: schools will be required to complete the analysis (A) and implications (I) as part of their ongoing evaluative practice.

| Question | Data |
| --- | --- |
| To what extent have teachers across the network effectively collaborated to share student information and prepare students for a smooth transition from primary to high school, supporting continuity of learning? | Student work samples, professional learning notes, orientation and transition activity plans, shared student profiles. |

## References

This resource contains NSW Curriculum and syllabus content. The NSW Curriculum is developed by the NSW Education Standards Authority. This content is prepared by NESA for and on behalf of the Crown in right of the State of New South Wales. The material is protected by Crown copyright.

Please refer to the NESA Copyright Disclaimer for more information https://educationstandards.nsw.edu.au/wps/portal/nesa/mini-footer/copyright.

NESA holds the only official and up-to-date versions of the NSW Curriculum and syllabus documents. Please visit the NSW Education Standards Authority (NESA) website https://educationstandards.nsw.edu.au/ and the NSW Curriculum website https://curriculum.nsw.edu.au.

Anderson LW, Jacobs J, Schramm S and Splittgerber F (2000) ‘School transitions: beginning of the end or a new beginning?’, International Journal of Educational Research, 33(4):325–339, accessed 17 April 2024.

CESE (Centre for Education Statistics and Evaluation) (2024) Transition to high school – What Works Best in practice, NSW Department of Education.

Galton M and McLellan R (2017) ‘A transition Odyssey: pupils’ experiences of transfer to secondary school across five decades’, Research Papers in Education, 33(2):1–23, accessed 17 April 2024.

Martin AJ, Collie RJ, Stephan M, Flesken A, Halcrow F and McCourt B (2024) ‘The role of teaching support in assisting students’ transition to high school’, Learning and Individual Differences, 109(102382), accessed 17 April 2024.

Martin AJ, Collie RJ, Stephan M, Flesken A, Halcrow F and McCourt B (2024) ‘What is the role of teaching support in students’ motivation and engagement trajectories during adolescence? A four-year latent growth modelling study’, Learning and Instruction, 92(101910), accessed 17 April 2024.

Sniedze S, Felgate R, O’Grady E, Buckley S and Lietz P (2021) ‘What Australian students say about transition to secondary school. Final report’, Australian Council for Educational Research, accessed 17 April 2024.

Symonds JE and Galton M (2014) ‘Moving to the next school at age 10–14 years: an international review of psychological development at school transition’, Review of Education, 2(1):1–27, accessed 17 April 2024.

Van Rens M, Haelermans C, Groot W and van den Brink HM (2018) ‘Facilitating a Successful Transition to Secondary School: (How) Does it Work? A Systematic Literature Review’, Adolescent Research Review, 3:43–56, accessed 17 April 2024.

© State of New South Wales (Department of Education), 2025

The copyright material published in this resource is subject to the Copyright Act 1968 (Cth) and is owned by the NSW Department of Education or, where indicated, by a party other than the NSW Department of Education (third-party material).

Copyright material available in this resource and owned by the NSW Department of Education is licensed under a Creative Commons Attribution 4.0 International (CC BY 4.0) license.

This license allows you to share and adapt the material for any purpose, even commercially.

Attribution should be given to © State of New South Wales (Department of Education), 2025.

Material in this resource not available under a Creative Commons license:

- the NSW Department of Education logo, other logos and trademark-protected material

- material owned by a third party that has been reproduced with permission. You will need to obtain permission from the third party to reuse its material.

Links to third-party material and websites

Please note that the provided (reading/viewing material/list/links/texts) are a suggestion only and implies no endorsement, by the New South Wales Department of Education, of any author, publisher, or book title. School principals and teachers are best placed to assess the suitability of resources that would complement the curriculum and reflect the needs and interests of their students.

If you use the links provided in this document to access a third-party's website, you acknowledge that the terms of use, including licence terms set out on the third-party's website apply to the use which may be made of the materials on that third-party website or where permitted by the Copyright Act 1968 (Cth). The department accepts no responsibility for content on third-party websites.