Phases of PBL Implementation

These implementation guidelines are designed to support coaches and PBL coordinators in the first phase of Universal Prevention. These steps are a guide and may not necessarily occur in the order in which they appear in this document.

| Step |  | Resources |
| --- | --- | --- |
| Establish Commitment and Readiness - Executive start-up meeting - Leadership support and approval - Principal support and commitment - 3 -5 year implementation target aligned with school plan - Whole staff ‘Taster’ -Minimum 80% staff commitment - School investment in PBL e.g. Budget allocation - TPL, signage, time commitment etc. |  | - PBL contact person - ‘PBL Accessing Universal Prevention’ document - ‘PBL Taster’ (conducted by PBL contact person) |
| Team Formation - Form representative, sustainable team that has decision-making authority. Include the Principal and representation from – school executive, each stage/faculty, Learning and Support team, SLSO, community/parent and student body Professional Learning Core team members including the principal undertake Universal Training delivered by PBL team (registered courses) Team Meetings - Establish regular meeting times (min. monthly) - Inform coach of meeting schedules - Allocate team roles – consider rotating annually - Ongoing – identify potential future team members - Develop protocols for team meetings - Develop an agenda template - Develop working agreements for meetings - Develop a minutes template - Agenda distribution process - Minutes distribution process Staff Communication - Consider ways to communicate to whole staff e.g. standing section in staff/team/faculty meetings, written updates etc. - Develop PBL staff noticeboard/ electronic display; - Action plan - Team roles/members - Expectations matrix - Meeting minutes - Graphed data - Current initiatives and focus areas - Staff feedback processes | Coach Identification - Identify internal/external coach to provide long-term support to the team - Coach training (unless already trained) - Join local coaching networks (if not already a member) | Teacher Professional Learning - ‘Tier 1 - Universal School-wide Systems’ - ‘PBL Coach Training’ Universal Training Resources - Suggested team roles |
| Data Based Action Plan Development - Develop annual PBL action plan aligned to school targets - Share action plan with team members and the coach - Utilise ongoing data collection to refine action plan and for current/future planning e.g. surveys, anecdotal, referrals, staff and student attendance - Internal - school based data used for decision making - External conducted by coach - SAS, TFI, SET, BoQ - Action plan updated regularly |  | Universal Training Resources - BoQ Action Plan - BoQ Coach Scoring Guide |
| Statement of Purpose - Initiate processes to develop a statement of purpose with all school staff - Consult all stakeholders – community and students - Ensure visibility of statement of purpose (newsletter, website, school app, school noticeboard etc.) |  | Universal Training Resources - PowerPoint presentation - sample statement of purpose |
| School Rules - Develop with consultation of all stakeholders 3 -5 positively stated rules - Consider strategies to communicate new rules to all stakeholders - Develop rule signage and other promotional material. Use budget signage while transitioning - Post signage including classrooms and a minimum of 3 other school settings - Consider strategies to promote rules – school policies and documents, noticeboards, newsletters, website, community events, social media etc. |  | Universal Training Resources - PowerPoint presentation – samples of expectations and signage |
| Expectation Matrix - Develop draft expectation matrix - Define school locations include; - All settings and others as applicable - Canteen/ toilets/ assembly/ hall/ office etc. - Consultation with all staff (allow 2 staff meetings) using samples and examples from other schools - Cross-reference OMPUA (Observable, Measureable, Positively Stated, Understandable, Always applicable) guidelines - Consider using focus groups – students and parents - Finalise matrix - Communicate matrix to all stakeholders (staff meeting, newsletter, assembly, staff/student handbook, diary, website, school app, social media). Use feedback to amend if necessary - Consider developing a consistency grid to support consistent staff practice - Matrix/sections of matrix displayed in all areas of the school - Staff matrix developed (if required) |  | Universal Training Resources - Expectation matrix samples - OMPUA Guidelines - Consistency grid samples |
| Social Skills Lessons - Select focus areas identified from expectations matrix - Lesson template identified - Planning time allocated to PBL team members and other interested staff to develop lessons - Lesson topics allocated to PBL team members and other staff - Lesson plans developed - Ongoing areas of lesson plan need identified through data and developed accordingly in consultation with staff as the need arises - System developed for staff to support new and returning students become oriented to school rules (rules, matrix, lessons etc.) |  | Universal Training Resources - Lesson template - PowerPoint presentation -Sample lessons plans |
| Acknowledgement System - Review current feedback system to ensure acknowledgement of positive behaviours as well as academic achievement - Student consultation using a variety of methods to ensure types of rewards have student currency - Parent/community consultation (optional) - Develop a ‘free and frequent’ method of reinforcement (both classroom and school-wide systems) e.g. raffle tickets, dojo points, stickers, certificates etc. - Staff orientation to new/revised system with specific guidelines e.g. How many? How often? Where? What behaviours to reinforce? - Develop a system of incentives for staff to encourage the use of acknowledgement system - Incorporate reward system in school documents e.g. – Student Wellbeing Policy, Discipline Policy, staff handbook etc. - Develop system to support casual and short-term staff understand the merit system including a visual flowchart |  | - Samples of school PBL handbooks - Samples of school policies that embed PBL |
| System for Discouraging Problem Behaviours - Identification of minor (classroom managed) and major (executive managed) behaviours identified in collaboration with staff, students and parent community - Behaviour management flowchart developed which includes proactive strategies, a redirection plan, and a range of consequences for minor (class teacher managed) and major (executive managed) behaviours - Schedule review of current incident referral (student name/grade, time/location of incident, referring staff, problem behaviour, persons involved, possible motivation and administration decision) to include key areas - Modify Level monitoring cards (if applicable) to include school rules and reflect behaviour management flowchart - Modify letters to parents to include school rules (if applicable) - Consultation/communication with parents and school community on the new behaviour system - Relevant policies and school documentation to be updated to include reviewed systems for discouraging problem behaviour e.g. Student Wellbeing Policy, staff handbook, professional learning, response strategies etc. |  | Universal Training Resources - Samples of behaviour management flowcharts - Sample behaviour referral forms |
| Staff Professional Learning – PBL School-wide Systems - Collaborate with all staff in the development of school-wide strategies - Whole staff professional learning PBL systems and practices– staff meetings and staff development days tied to targets within the PBL Action Plan - Staff self-evaluation of own supervision practices to ensure supervision practices involve modelling of appropriate behaviours - Prompt cards/scripts/consistency grid provided to staff to reinforce school rules |  | Universal Training Resources - Staff self-evaluation |
| Data Based Decision Systems - Timeline established for annual external data collection tools (SAS, SET, BoQ, TFI) - Establish electronic data collection system including all features of referral form (student name/grade, time/location of incident, referring staff, problem behaviour, persons involved, possible motivation and administration decision) - Discipline referral form is compatible with data entry system (if required) - Multiple staff members are able to enter data – release time allocated where required - Discipline data is used by the PBL team at least twice per team to make decisions when evaluating, designing and implementing school-wide behaviour support - Discipline data is provided to staff at least three times per year (Noticeboard/ team meetings/ professional learning etc.) - Consider using ‘Big 5 Data’ to support data collection |  | Universal Training Resources - ‘Big 5 Data Decision Guide’ |
| Embedding PBL Values and Expectations - Review and update relevant policies and school documentation e.g. school wellbeing and discipline policy - Incorporate PBL as a standing item at staff/exec. meetings - Ensure all staff have ready access to PBL minutes/action plan - Consider planning and implementing a launch day to introduce school rules and behavioural expectations. Schedule these regularly for example annually, biennial - Schedule regular focus days throughout the year - Consider ways to embed/reinforce school rules in school assemblies and use these to celebrate student social/academic success - Embed PBL in school newsletter/website/apps etc. e.g. updates, data improvements, student awards - Update teacher handbook to include changes to wellbeing and discipline policy. - Consider developing a PBL staff handbook. - Produce promotional materials e.g. stickers, pencils, school diaries to promote PBL in the school - Promotional material developed such as movie for front office, website, parent newsletter etc. explaining PBL and giving examples of what this means in your school - Conduct regular signage audits to ensure signage is maintained and updated over time - PBL logo/images are used on letterheads, school’s website etc. - PBL framework is used to strengthen other wellbeing initiatives within the school e.g. peer mediation, anti-bullying and values education - Regular professional development for staff is provided on PBL (current research, workshops, key readings, booster sessions on rewards/referrals etc.) |  |  |
| Development and Implementation of Bullying Prevention Plan - Develop a school-wide consistent definition of bullying that includes cyber bullying - Survey staff and students to identify safe and unsafe areas within the school using a customized survey or other e.g. ‘Tell Them From Me’, ‘Kids/Mind Matters’, Friendly Schools Plus - Use school data about bullying behaviours to develop a consistent and reliable reporting system for victims, bullies and bystanders (may include web based procedures) - Teach students social and emotional competencies to promote pro-social behaviour - Teach student strategies for safely intervening in bullying situations and using the reporting system - Provide professional learning to all staff regarding active supervision of non/classroom areas - Secure/monitor identified ‘unsafe’ areas - Review consequences for bullying, ensuring preventative measures are in place - Set-up protocols for collecting information from parents and informing parents of repeated bullying incidents (bully and victim) |  | - Safe Schools Hub http://safeschoolshub.edu.au/ |

Adapted from ‘PBIS Implementation Processes’ (Fixsen, Naoom, Blase, Friedman & Wallace, 2005), ‘Positive Behaviour for Learning – An Implementer’s Guide for PBL Coaches’ (NSW DoE), ‘BoQ Coach Scoring Guide’ (Adapted by Western Sydney Region - PBL, 2012)